## System Requirements
Sports Center Management System – System Requirements
BA baseline: scope, roles, permissions, business rules and quality requirements. Status is proposed and not yet implemented.
Requirement ID | Category | Role | Requirement | Priority | Target phase | Acceptance criteria | Status
FR-001 | Authentication | All | Users can sign in and sign out securely. | Must | MVP | Valid credentials create a session; invalid credentials show an error without revealing which field was wrong. | Proposed
FR-002 | Authorization | All | The system enforces role and permission checks on every protected API. | Must | MVP | A user cannot access or mutate an endpoint outside the assigned permission, even by calling the API directly. | Proposed
FR-003 | User management | Manager | Manager can create, update, suspend and reactivate staff accounts. | Must | MVP | Suspended staff cannot sign in; every status change is logged. | Proposed
FR-004 | Member management | Manager, Receptionist | Staff can create and maintain member profiles. | Must | MVP | Required fields are validated and duplicate member records are prevented. | Proposed
FR-005 | Membership | Manager, Receptionist, Member | The system manages membership packages, inherited entitlements by package tier, payment-gated activation, expiry and grace status. | Must | MVP | Higher-priced packages include every lower-tier entitlement; a membership becomes active only after successful payment; expiry and grace timestamps are auditable. | Proposed
FR-006 | Class management | Manager, Coach | Manager creates classes; Coach may propose schedule changes for assigned classes. | Must | MVP | Class capacity, coach, room and schedule are validated before publishing. | Proposed
FR-007 | Registration | Member, Receptionist | Member or Receptionist can register or cancel a class booking. | Must | MVP | Expired members, duplicate bookings and full classes are rejected with a clear reason. | Proposed
FR-008 | Attendance | Coach, Member | Coach records class attendance; Member sees own history. | Must | MVP | Coach records present, absent or late for assigned classes. Corrections require a reason and create an audit log. | Updated
FR-009 | Training plans and progress | Coach, Member | Coach creates and maintains multi-exercise personal training plans for assigned Members, then records results and comments. Member views only their own plans and results. | Must | MVP | An MVP plan stores its name, goal, start and end dates plus one or more exercises. Each exercise has a name, sets, repetitions or duration, rest time and an optional note. Coach can edit only assigned Members; Member cannot edit Coach records. | Updated
FR-010 | Payments | Manager, Receptionist, Member | The system records manual or simulated payments and transaction status for memberships. | Must | MVP | Each payment has amount, method, payer, membership, paid timestamp and immutable transaction history. Only a successful payment activates a membership. | Proposed
FR-011 | Reporting | Manager | Manager dashboard summarizes center-wide revenue, members, classes, bookings and attendance for a selected day, week, month, quarter or year. It compares each KPI with the immediately preceding equivalent period and provides role-scoped operational summaries for other users. | Should | MVP | Changing the period refreshes every dashboard KPI and trend. Each comparison uses the immediately preceding period of equal duration. Revenue uses paid_at for confirmed cash payments only; pending payments and memberships expiring within 7 days remain visible as actionable alerts. | Updated
FR-012 | Notifications | All | The system provides in-app notifications for membership expiry, grace period and important class events. | Should | Version 1 | From 7 days before contractual expiry, the Member receives a daily renewal reminder. The reminder continues through the 72-hour grace period and respects role scope and preferences. | Proposed
FR-013 | Support | Member, Receptionist, Manager | Member submits support requests and staff track status and response. | Should | Version 1 | Each request has owner, status, timestamps and response history. | Proposed
FR-014 | Refund workflow | Out of scope | Member refund requests are not supported after contract acceptance and use of the membership. | Out of scope | Out of scope | The product exposes no member-facing refund workflow. Any future financial reversal requires a separate approved policy. | Rejected by policy
FR-015 | AI assistance | Coach, Member | AI uses schedule, booking, attendance, training-plan and membership-expiry context to assist Coach and Member with reminders and Coach-reviewed guidance. | Nice | Version 1 | AI is not an open-ended live chatbot or medical adviser. Coach approval is required before AI-generated training guidance is sent to a Member. | Proposed
NFR-001 | Security | System | Passwords are securely hashed; sessions, rate limits and access logs are managed. | Must | MVP | Password hashes are never exposed; repeated failed login attempts are limited and logged. | Proposed
NFR-002 | Privacy | System | Personal and health-related data are restricted by role and purpose. | Must | Version 1 | Users can access only the minimum data needed for their workflow. | Proposed
NFR-003 | Reliability | System | The system has backup, restore and error logging procedures. | Must | Production | A backup can be restored in a test environment and restore results are recorded. | Proposed
NFR-004 | Performance | System | Core pages and APIs respond within an agreed target under expected load. | Should | Version 1 | Performance tests document response time at the agreed concurrent-user target. | Proposed
NFR-005 | Auditability | System | Sensitive actions are recorded with actor, time, action and affected record. | Must | MVP | Role changes, payment adjustments, facility check-ins and attendance corrections have audit entries. | Proposed
Role and permission summary
Role | View scope | Create | Update | Approve | Restricted actions
Center Manager | All center data | Users, classes, packages | Operational settings | Class publication | Should not silently delete financial history or bypass payment/audit controls
Coach | Assigned classes and students | Plans, exercises, results, comments | Own assigned records | None | Cannot access payment administration
Member | Own profile, package and history | Bookings, support requests | Own profile | None | Cannot view other members' private data
Receptionist | Members and front-desk workflows | Members, bookings, payments | Operational member data | None | Cannot approve refunds, alter settled transactions or bypass membership activation rules
Core business rules
Rule ID | Area | Rule | Reason / expected outcome
BR-001 | Membership | A Member cannot book a class or check in when the membership is pending payment, expired or cancelled. | Prevents use before payment and after entitlement ends.
BR-002 | Registration | A Member cannot book the same class more than once. | Prevents duplicate bookings.
BR-003 | Capacity | A class cannot exceed its configured capacity. | Protects room and service capacity.
BR-004 | Attendance | A Coach may correct attendance immediately only with a reason; the correction creates an audit entry. | Preserves operational accountability without an approval queue.
BR-005 | Refund | Member-facing refund requests are out of scope after contract acceptance and membership use. | Avoids presenting an unsupported cancellation/refund promise.
BR-006 | Coach scope | A Member has one active primary Coach at a time. Coach access is limited to assigned Members and classes. | Protects member privacy and defines coaching ownership.
BR-007 | Package entitlement | Every higher-priced package includes all entitlements of lower-priced packages. Limits are evaluated by the entitlement rule, for example weekly group-class quota. | Makes package value and access decisions deterministic.
BR-008 | Payment activation | A membership remains pending payment until a successful payment. Successful payment activates it; pending or failed payment does not. | Separates login access from paid service access.
BR-009 | Expiry and renewal | Renewal reminders begin 7 days before contractual expiry and continue daily. If not renewed, access continues for exactly 72 hours after contractual expiry, then becomes expired automatically with no late fee. | Defines automatic renewal grace and notification timing.
BR-010 | Check-in | Facility check-in records entrance time and active membership entitlement. It is distinct from class attendance. | Keeps front-desk and class operations traceable.
BR-011 | Class scheduling | A class session is a concrete dated occurrence. Recurring class templates are optional and may be introduced after MVP. | Allows a single occurrence to be changed or cancelled without affecting other dates.
BR-012 | Revenue reporting | Revenue includes only payments with successful status and uses the successful payment timestamp. Pending, failed and reversed states are reported separately. | Prevents inflated revenue figures.
BR-013 | AI assistance | AI may generate reminders and Coach-reviewed guidance from operational context. It must not provide medical diagnosis or autonomously send a training plan. | Keeps AI assistive and Coach-led.

## MVP
Sports Center Management System – MVP task plan
Goal: prove the core operating workflow for one sports center with controlled scope. Tasks are derived from the requirement IDs in System Requirements.
Task ID | Source requirement IDs | Workstream | Task | Deliverable / scope | Owner | Dependencies | Priority | Acceptance criteria | Status
MVP-001 | FR-001, NFR-001 | Authentication | As a user, I can sign in and sign out. | Email/username, password, session | Backend + Security | User model | Must | Correct credentials open the correct role landing page; invalid credentials are rejected. | Planned
MVP-002 | FR-002, NFR-005 | Authorization | As the system, I enforce role permissions server-side. | Four roles and protected APIs | Backend + QA | Authentication | Must | Direct API access outside the role returns an authorization error. | Planned
MVP-003 | FR-003, FR-004 | Users | Manager can manage basic staff and member profiles. | Create, view, update, suspend | Backend + Frontend | Authorization | Must | Required fields validate and suspended staff cannot sign in. | Planned
MVP-004 | FR-005 | Membership | Staff can create and manage tiered membership packages and memberships. | Inherited package entitlements, pending-payment activation, contractual expiry and 72-hour grace period | Backend + Frontend | Users | Must | Higher tiers inherit lower-tier entitlements. Only successful payment activates access; expired access is blocked after exactly 72 grace hours. | Planned
MVP-005 | FR-006 | Classes | Manager can create classes with coach, room, schedule and capacity. | Single center, recurring schedule optional | Backend + Frontend | Users | Must | Invalid overlaps and missing required data are rejected. | Planned
MVP-006 | FR-007 | Bookings | Member or Receptionist can book and cancel classes. | No duplicate booking; capacity check | Backend + Frontend | Membership, Classes | Must | Full, expired and duplicate cases show clear errors. | Planned
MVP-007 | FR-008 | Attendance | Coach records class attendance and Member sees own history. | Present, absent, late; Coach correction with reason and audit | Backend + Frontend | Bookings | Must | Only assigned Coach records attendance. Coach corrections retain actor, reason and previous/new values. | Updated
MVP-008 | FR-009 | Training plans | Coach creates multi-exercise personal plans and records a result for an assigned Member. | Plan details plus one or more exercise items: name, sets, repetitions or duration, rest time and optional note. One general result and Coach comment per recorded date. | Backend + Frontend | Users, Classes | Must | A plan cannot be saved without an exercise. Coach can add, edit, remove and order exercises for an assigned Member. Member can view the plan and results but cannot alter Coach records. | Updated
MVP-009 | FR-010 | Payments | Receptionist records manual or simulated package payment. | No live payment gateway; payment success activates the linked membership | Backend + Finance | Membership | Must | A successful transaction includes amount, method, payer, membership and paid timestamp, then activates the membership. Pending/failed payment never activates access. | Planned
MVP-010 | FR-011 | Dashboard | Manager can review center performance and compare it with the prior equivalent period. | Period selector: day, week, month, quarter and year; four KPI cards, revenue trend and actionable alerts. Receptionist, Coach and Member receive only role-scoped summaries. | Frontend + QA | All core modules | Should | Changing the period updates all metrics. Revenue includes confirmed cash payments only; each KPI shows the comparison with the immediately preceding equivalent period. Pending cash receipts and memberships expiring within 7 days open their related lists. | Updated
MVP-011 | NFR-005 | Audit | System logs sensitive actions. | Role change, payment, attendance correction | Backend + Security | Authorization | Must | Log includes actor, action, timestamp and target record. | Planned

## Version 1
Sports Center Management System – Version 1 task plan
Goal: make the system usable in daily operations at one real center. Tasks are derived from the requirement IDs in System Requirements.
Task ID | Source requirement IDs | Workstream | Task | Deliverable / scope | Owner | Dependencies | Priority | Acceptance criteria | Status
V1-001 | FR-005 | Membership | System automates renewal reminders and membership expiry grace. | Daily reminders from 7 days before contractual expiry; exactly 72 hours grace after expiry; no late fee | Backend + Frontend | MVP membership, Notifications | Must | System sends daily reminders, preserves contractual expiry, calculates grace end at expiry plus 72 hours and expires access automatically if unpaid. | Planned
V1-002 | FR-007 | Bookings | The system supports waitlists and cancellation rules. | Capacity and cutoff policy | Backend + Frontend | MVP bookings | Must | Eligible waitlisted users are promoted according to a defined rule. | Planned
V1-003 | FR-010 | Payments | System supports real payment status and invoices. | Gateway integration, receipt history | Backend + Finance | MVP payments | Must | Success, failure, pending and refund states are handled safely. | Planned
V1-004 | FR-014 | Refunds | Member-facing refunds are excluded by business policy. | Keep no refund request or approval flow in product scope | Business policy | None | Out of scope | No member-facing refund request, approval or refund dashboard is delivered. Any future reversal requires a separately approved policy. | Rejected by policy
V1-005 | FR-008 | Front desk | Facility check-in is excluded by operating scope. | No entrance check-in flow is required for Receptionist. | Business policy | None | Out of scope | The product provides no facility check-in flow. Class attendance remains Coach-led under FR-008. | Rejected by policy
V1-006 | FR-012 | Notifications | Users receive relevant class and package notifications. | In-app plus optional email/push | Backend + Frontend | All core modules | Should | Notification preferences and role scope are respected. | Planned
V1-007 | FR-013 | Support | Member submits support ticket and tracks responses. | Open, assigned, in progress, resolved | Backend + Frontend | Authorization | Should | Ticket history is visible to authorized parties. | Planned
V1-008 | FR-011 | Reports | Manager views operational reports by date and coach. | Members, attendance, revenue, utilization | Backend + Frontend | Payments, Attendance | Should | Reports reconcile to source records and export if required. | Planned
V1-009 | NFR-001, NFR-002 | Security | System includes password management, rate limit and privacy controls. | Session and personal-data protection | Backend + Security | MVP authentication | Must | Sensitive data is minimized and repeated failed login attempts are controlled. | Planned
V1-010 | FR-015 | AI assist | AI assists Coach and Member with operational reminders and Coach-reviewed guidance. | Schedule, booking, attendance, plan and expiry context; no open-ended live chatbot or medical diagnosis | AI/Backend + Coach | Progress, Notifications | Nice | AI suggestions are labelled, Coach-reviewed before delivery to Member and never silently replace Coach judgment. | Planned
V1-011 | NFR-003 | Backup | Team can back up and test-restore operational data. | Documented restore procedure | DevOps | Database | Must | A restore test produces a recorded result and identified recovery time. | Planned
V1-012 | FR-009 | Training plans | Coach organizes a plan into workout sessions and tracks each session's completion. | Ordered sessions with title and optional scheduled date. Each session contains exercises. Coach records completed or skipped status and a session comment. | Backend + Frontend | MVP training plans | Should | A Coach can reorder sessions and exercises. Completing or skipping a session keeps its timestamp and Coach comment. Member sees only their own session status and feedback. | Proposed

## Production
Sports Center Management System – Production task plan
Goal: operate securely and reliably at scale, with support, monitoring and recovery controls. Tasks are derived from the requirement IDs in System Requirements.
Task ID | Source requirement IDs | Workstream | Task | Deliverable / scope | Owner | Dependencies | Priority | Acceptance criteria | Status
PROD-001 | FR-002, NFR-002 | Scale | System supports multiple branches or tenants with isolated data scope. | Branch-aware users, classes and reports | Architecture + Backend | Version 1 authorization | Must | A user cannot access records belonging to another branch without explicit permission. | Planned
PROD-002 | NFR-001 | Security | Production uses MFA for privileged users and hardened session controls. | Manager/admin protection | Backend + Security | Version 1 security | Must | Privileged access requires the configured second factor and secure session policy. | Planned
PROD-003 | NFR-003 | Observability | Team monitors uptime, errors, latency and failed jobs. | Dashboards, alerts and logs | DevOps | Deployment platform | Must | Critical failures create actionable alerts and retain correlation details. | Planned
PROD-004 | NFR-003 | Recovery | System has automated backups and disaster-recovery procedures. | RPO/RTO documented | DevOps | Version 1 backup | Must | Restore drills meet the agreed recovery targets. | Planned
PROD-005 | NFR-004 | Performance | System passes load and stress tests for expected peak usage. | Peak booking/check-in periods | Backend + QA | Stable V1 flows | Must | Core workflows stay within agreed response-time thresholds under target load. | Planned
PROD-006 | NFR-003 | Delivery | Team uses staging, CI/CD, approvals and rollback. | Release governance | DevOps | Monitoring | Must | A failed release can be rolled back using a tested procedure. | Planned
PROD-007 | NFR-002 | Privacy | System applies retention, consent and deletion procedures. | Personal and health-related data | Security + BA | Security, Legal policy | Must | Users can exercise approved privacy requests and access is auditable. | Planned
PROD-008 | FR-010, NFR-005 | Payments | Financial operations have reconciliation and audit controls. | Successful transactions, payment-status reporting and exports | Backend + Finance | Version 1 payments | Must | Daily revenue totals reconcile successful provider payments to internal payment events; pending and failed states reconcile separately. | Planned
PROD-009 | NFR-003 | Support | Operations team has incident, support and escalation procedures. | SLA and user support | Backend + Frontend | Monitoring | Should | Incidents have severity, owner, response and resolution records. | Planned
PROD-010 | NFR-001, NFR-002 | Integrations | Approved external integrations are managed with scoped credentials. | Payment, email, health apps if needed | Backend + Security | Security review | Nice | Credentials are stored securely, rotated and limited to required permissions. | Planned
PROD-011 | FR-009, NFR-004 | Training analytics | System tracks progressive training performance and plan adjustments over time. | Actual load, achieved sets/repetitions or duration, optional effort rating, progress charts and plan version history. | Backend + Frontend + QA | Version 1 training sessions | Should | Trend charts use recorded performance data. Each plan adjustment is traceable to a version and timestamp. Coach scope and Member privacy remain enforced. | Proposed